# MEETING NOTES

Nobler Works

# Marketing Campaign Planning - Q2 Launch

| Date: | January 29, 2025 |
| --- | --- |
| Time: | 3:00 PM - 4:30 PM EST |
| Location: | Conference Room B |
| Facilitator: | Olivia Bennett, Marketing Director |
| Note Taker: | Jason Liu, Content Marketing Manager |
| Attendees: | Olivia Bennett, Jason Liu, Maya Thompson (Demand Gen Manager), Derek Walsh (Digital Marketing Specialist), Alicia Moreno (Brand Designer), Rachel Foster (VP Sales - guest) |
| Absent: | None |

Meeting Purpose: Plan and align on Q2 product launch campaign strategy, creative direction, timeline, and deliverables.

## Campaign Overview

Olivia opened the meeting by reviewing the campaign objectives for the Q2 product launch (Project Phoenix).

Campaign Goals:

- Generate 500 qualified leads in first 30 days post-launch

- Achieve 5,000 website visits to product landing page

- Secure 10 media mentions in industry publications

- Drive 200 demo requests within first month

- Build awareness with target audience (IT Directors and CTOs at mid-market companies)

Budget Allocation:

- Total campaign budget: $85,000

- Digital advertising: $35,000

- Content creation: $25,000

- Events and webinars: $15,000

- PR and influencer outreach: $10,000

## Creative Direction & Messaging

Alicia presented initial creative concepts and the team discussed messaging approach.

Key Messaging Themes:

- Primary: "Transform Your Operations in Half the Time"

- Secondary: "The Next Generation of Enterprise Solutions"

- Supporting: Focus on ease of implementation, cost savings, and scalability

Design Approach:

Alicia showed three design directions - the team preferred Option 2 (modern, bold colors with clean typography). The design emphasizes speed and efficiency through visual metaphors.

Discussion Points:

- Rachel suggested highlighting customer pain points more prominently. Sales team hears repeatedly about implementation complexity and long timelines - this should be front and center.

- Maya recommended A/B testing two headline variations to optimize conversion rates.

- Derek noted we should ensure all creative assets are optimized for mobile since 62% of our site traffic is mobile.

Decision: Proceed with Option 2 design direction. Alicia to incorporate feedback and present revised concepts by Feb 5. Team agreed to test two headline variations in paid ads.

## Multi-Channel Strategy

Maya and Derek outlined the integrated channel approach for maximum reach and engagement.

### Digital Advertising

Derek will lead digital campaigns across multiple platforms:

- Google Ads (Search & Display) - $18,000 budget

- LinkedIn Sponsored Content - $12,000 budget (primary channel for B2B targeting)

- Retargeting campaigns - $5,000 budget

- Launch window: April 1-30 with option to extend based on performance

### Content Marketing

Jason outlined the content plan to support the launch:

- Launch blog post (2,000 words) - Jason writing

- Product comparison guide - partner with sales for competitive intel

- Case study featuring beta customer (CloudNine Systems) - interview scheduled

- Explainer video (90 seconds) - working with external agency

- Email nurture series (5 emails) - draft by Feb 15

- Social media content calendar (30 posts) - mix of educational and promotional

Note: Rachel emphasized the case study is critical - sales needs real-world proof points for conversations. Jason confirmed interview is scheduled for Feb 7 and will fast-track production.

### Events & Webinars

Maya proposed event strategy:

- Launch webinar: April 10 (product demo + Q&A with CTO)

- Industry conference booth: TechSummit 2025 (April 22-24)

- Virtual roundtable with customers: Late April (invite beta customers to share experiences)

Team discussed whether to host multiple webinars vs. one large event. Decided on single launch webinar with strong promotion, then smaller follow-up sessions based on demand.

### PR & Media Outreach

Olivia will lead PR efforts:

- Press release distributed via PR Newswire - April 1

- Pitch to 20 target publications (TechCrunch, VentureBeat, industry trades)

- Briefings with 5 key analysts and influencers

- Guest article placements (2-3 bylined articles from leadership)

## Campaign Timeline & Milestones

| Date/Week | Milestone / Deliverable | Owner |
| --- | --- | --- |
| Feb 5 | Revised creative concepts ready | Alicia |
| Feb 15 | All content drafts completed | Jason |
| Feb 20 | Case study finalized | Jason |
| Mar 1 | Product landing page live | Derek |
| Mar 10 | Explainer video delivered by agency | Alicia |
| Mar 15 | Ad campaigns set up and tested | Derek |
| Mar 20 | Press release and media kit finalized | Olivia |
| Mar 25 | Sales enablement materials ready | Jason & Rachel |
| April 1 | 🚀 CAMPAIGN LAUNCH DAY | All Team |
| April 10 | Launch webinar | Maya |

## Measurement & Success Metrics

Maya outlined how we'll track campaign performance and report on results.

Weekly Metrics (reported every Monday):

- Landing page traffic and conversion rate

- Lead volume and quality scores

- Demo requests

- Ad performance (CTR, CPC, conversions)

- Social engagement metrics

Monthly Deep Dive (first Monday of each month):

- Full funnel analysis

- Content performance by piece

- Channel ROI analysis

- Pipeline contribution

Derek will set up Google Analytics dashboard and Maya will create weekly reporting template by Feb 8.

## Risks & Contingency Planning

The team identified potential risks and backup plans:

Risk: Product launch date slips from April 1

Mitigation: Campaign is designed with 2-week flexibility. Can shift launch to April 15 without major impact. All dated materials will use week references rather than specific dates.

Risk: Case study customer backs out

Mitigation: Have two backup beta customers identified. Can pivot to generic success metrics and testimonials if needed.

Risk: Ad performance underperforms in first week

Mitigation: Have additional creative variations ready to test. Can reallocate budget to best-performing channels. Reserved 15% of budget for optimization.

## Team Feedback & Questions

Rachel (Sales): Can we get the sales team involved earlier in content review? We want to ensure messaging resonates with actual customer conversations.

Response: Olivia agreed - will include Rachel in Feb 5 creative review and sales team will review all content before finalization.

Derek: Should we be running dark posts on social to test messaging before launch?

Response: Great idea - approved to allocate $2K from digital budget for pre-launch testing in March.

Jason: Do we need to coordinate with customer success on any support materials for new customers?

Response: Yes - Olivia will connect with Maria (CS Director) to ensure onboarding materials are ready.

## Action Items

| Action Item | Owner | Due Date |
| --- | --- | --- |
| Present revised creative concepts incorporating team feedback | Alicia Moreno | Feb 5 |
| Complete case study interview with CloudNine Systems | Jason Liu | Feb 7 |
| Set up Google Analytics dashboard and tracking | Derek Walsh | Feb 8 |
| Create weekly reporting template for campaign metrics | Maya Thompson | Feb 8 |
| Coordinate with Customer Success on onboarding materials | Olivia Bennett | Feb 10 |
| Draft all content pieces (blog, emails, social posts) | Jason Liu | Feb 15 |
| Include sales team in creative review session | Olivia Bennett | Feb 5 |
| Launch dark post testing on social media | Derek Walsh | Mar 1 |

Next Meeting:

Campaign Progress Check-In - February 15, 2025 at 3:00 PM EST

Meeting adjourned:

4:30 PM EST

Notes prepared by:

Jason Liu, Content Marketing Manager